## Read Me
Risk Register and Heat Map
A free tool from CyberAbeer, cyberabeer.com
This workbook gives you a working risk register in minutes: score risks by likelihood and impact, see them plotted on a heat map, and track treatment through to a residual score, without setting up software or a subscription.
How to use this workbook
1. Open the Risk Register tab. Replace the 10 sample rows with your own risks, or add rows below them.
2. Fill in the columns shaded light yellow: Reference, Risk, Category, Description, Owner, Likelihood, Impact, Treatment, and the residual (post-treatment) scores.
3. Inherent Score, Inherent Rating, Residual Score, and Residual Rating calculate automatically. Do not type into those columns.
4. Open the Heat Map tab to see how your risks are distributed across likelihood and impact, and the Dashboard tab for a one-page summary by status and category.
5. Save a copy before you start, and update review dates as risks are reassessed.
Scoring legend
Likelihood and Impact are each scored 1 to 5. The score for a risk is Likelihood x Impact, from 1 (lowest) to 25 (highest).
Score | Rating | What it means
1 to 4 | Low | Accept and monitor at routine review cycles.
5 to 9 | Medium | Assign an owner and a treatment plan with a realistic timeline.
10 to 15 | High | Requires active treatment and regular management visibility.
16 to 25 | Critical | Escalate immediately; treat as a priority for leadership.
This tool is provided free as part of CyberAbeer's practical GRC resources. It is a starting framework, not a substitute for a formal risk assessment methodology or legal, security, or compliance advice.

## Risk Register
Ref | Risk | Category | Description | Owner | Likelihood (1-5) | Impact (1-5) | Inherent Score | Inherent Rating | Treatment | Residual Likelihood (1-5) | Residual Impact (1-5) | Residual Score | Residual Rating | Status | Next Review
R-01 | Ransomware attack on file servers | Information Security | Malicious encryption of shared drives via phishing-delivered payload, halting operations. | IT Security Manager | 3 | 5 | 15 | High | Mitigate | 2 | 4 | 8 | Medium | Open | 2026-09-15
R-02 | Third-party vendor data breach | Third Party | A cloud vendor holding customer data suffers a breach that exposes our records. | Procurement Lead | 3 | 4 | 12 | High | Mitigate | 2 | 3 | 6 | Medium | Open | 2026-10-01
R-03 | Unpatched critical vulnerability exploited | Information Security | A known CVE on an internet-facing system remains unpatched past SLA and is exploited. | IT Operations | 4 | 4 | 16 | Critical | Mitigate | 2 | 3 | 6 | Medium | Treated | 2026-08-20
R-04 | Phishing leads to credential compromise | Information Security | Employee clicks a phishing link and reuses a password across corporate systems. | CISO | 4 | 3 | 12 | High | Mitigate | 2 | 3 | 6 | Medium | Monitoring | 2026-09-01
R-05 | Insider misuse of privileged access | Operational | A privileged user accesses or exports data outside their job responsibilities. | HR and IT Security | 2 | 4 | 8 | Medium | Mitigate | 1 | 4 | 4 | Low | Open | 2026-11-05
R-06 | Cloud storage misconfiguration exposes data | Information Security | A storage bucket or database is left publicly accessible due to a configuration error. | Cloud Engineering Lead | 3 | 4 | 12 | High | Mitigate | 1 | 4 | 4 | Low | Treated | 2026-08-30
R-07 | Regulatory non-compliance fine | Compliance | Failure to meet a data protection or industry regulation results in a financial penalty. | Compliance Officer | 2 | 4 | 8 | Medium | Accept | 2 | 4 | 8 | Medium | Monitoring | 2026-12-01
R-08 | Business continuity plan failure during outage | Operational | A major system outage occurs and the recovery plan does not meet the recovery time objective. | Business Continuity Manager | 2 | 5 | 10 | High | Mitigate | 1 | 4 | 4 | Low | Open | 2026-10-15
R-09 | Loss of key personnel with critical knowledge | Strategic | Departure of a specialist staff member with undocumented processes disrupts operations. | People Operations | 3 | 3 | 9 | Medium | Mitigate | 2 | 2 | 4 | Low | Monitoring | 2026-09-20
R-10 | Weak access control on legacy application | Information Security | A legacy system lacks role-based access control, allowing broader access than required. | Application Owner | 3 | 3 | 9 | Medium | Mitigate | 2 | 2 | 4 | Low | Open | 2026-09-25
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low
[7 empty] | 0 | Low |  |  |  | 0 | Low

## Heat Map
Inherent Risk Heat Map
Count of risks by likelihood and impact, from the Risk Register tab (Inherent scores).
Impact
Likelihood | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 1 | 1 | 0
3 | 0 | 0 | 2 | 2 | 1
2 | 0 | 0 | 0 | 2 | 1
1 | 0 | 0 | 0 | 0 | 0
Each cell shows how many risks currently sit at that likelihood and impact combination.
Risk count by inherent rating
Critical (16-25) | 1
High (10-15) | 5
Medium (5-9) | 4
Low (1-4) | 40

## Dashboard
Risk Register Dashboard
Live summary calculated from the Risk Register tab.
Total risks logged | 10 | By status
High or Critical (residual) | 0 | Open | 5
Open risks | 5 | Treated | 2
|  | Monitoring | 3
|  | Closed | 0
By category
Information Security | 5
Operational | 2
Compliance | 1
Financial | 0
Strategic | 1
Third Party | 1
Privacy | 0